Northgate Depot Relocation

Project Brief, Version 1.0, drafted 4 August 2026

1. Purpose

This brief sets out the case for relocating depot operations from Northgate to the Calder Park site.

The relocation is driven by the expiry of the Northgate lease in March 2028.

2. Scope

The programme covers the following work streams:

- Site acquisition and planning consent

- Design and construction of the main warehouse

- Fleet transition and driver relocation

- Disposal of surplus racking and shelving

- Systems cutover, including the warehouse management platform

Assumptions

The figures in this brief assume that planning consent is granted without a public inquiry, and that steel prices remain within ten percent of the June 2026 index.

A contingency of ten percent has been applied to all construction lines.

Budget and Milestones

All figures are in thousands of pounds and exclude VAT.

| Work package | Owner | Budget | Due |
| --- | --- | --- | --- |
| Land and legal | R. Okafor | 1,450 | Q4 2026 |
| Warehouse construction | S. Lindqvist | 8,200 | Q3 2027 |
| Fleet transition | M. Bahri | 640 | Q4 2027 |
| Surplus racking disposal | M. Bahri | 75 | Q1 2028 |
| Systems cutover | D. Whitfield | 310 | Q1 2028 |

Total programme cost is estimated at 10,675 thousand pounds before contingency.

Risks

Principal risk: refusal of planning consent, which would push the construction start beyond the lease expiry date.

Secondary risks include driver attrition during the transition and the availability of long lead mechanical plant.