Northgate Depot Relocation

Project Brief, Version 2.0, reviewed 18 September 2026

1. Purpose

This brief sets out the case for relocating depot operations from Northgate to the Calder Park site, and records the decisions taken at the September review board.

The relocation is driven by the expiry of the Northgate lease in March 2028 and by persistent capacity constraints on the loading apron.

Nothing in this brief commits the company to a construction contract; that decision sits with the board in Q1 2027.

2. Scope

The programme covers the following work streams:

- Site acquisition and planning consent

- Design and construction of the main warehouse and the ancillary workshop

- Fleet transition and driver relocation

- Decommissioning and environmental survey of the Northgate site

- Systems cutover, including the warehouse management platform

Budget and Milestones

All figures are in thousands of pounds and exclude VAT.

| Work package | Owner | Budget | Due |
| --- | --- | --- | --- |
| Land and legal | R. Okafor | 1,510 | Q4 2026 |
| Warehouse construction | S. Lindqvist | 9,050 | Q4 2027 |
| Ancillary workshop | S. Lindqvist | 1,120 | Q4 2027 |
| Fleet transition | M. Bahri | 640 | Q4 2027 |
| Systems cutover | D. Whitfield | 295 | Q2 2028 |

Total programme cost is estimated at 12,615 thousand pounds before contingency.

Assumptions

The figures in this brief assume that planning consent is granted without a public inquiry, and that steel prices remain within ten percent of the June 2026 index.

A contingency of fifteen percent has been applied to all construction lines.

Risks

Principal risk: refusal or delay of planning consent, which would push the construction start beyond the lease expiry date.

Secondary risks include driver attrition during the transition and the availability of long lead mechanical plant.

Approvals

Reviewed by the September board. Approved to proceed to outline design, subject to the revised contingency.